## Main
| Today | Copy this doc and follow the link below for instructions. |  |  | 106 | 36 |  |  |  | 14 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 2017-02-08 | http://bazald.com/eecs-494/burndown |  |  | Hours | Hours | Hours |  |  | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Bug Statuses are used below in the bug area | Bug
# | Rank | Task | Assn | Assist | Est. | Rem. | Worked |  |  | 2017-02-01 | 2017-02-02 | 2017-02-03 | 2017-02-04 | 2017-02-05 | 2017-02-06 | 2017-02-07 | 2017-02-08 | 2017-02-09 | 2017-02-10 | 2017-02-11 | 2017-02-12 | 2017-02-13 | 2017-02-14 | 2017-02-15 | Detailed Information | Status
Task Assignments | [25 empty] | Reported
|  | Mechanism design | YZ | [22 empty] | Can't Repro
1 | 1 | Initial mechanism design | YZ |  | 8 | 0 |  |  | 8 | 6 | 6 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | movement of weapon controls movement of hero
2 | 2 | Discuss mechanism design with other people | YZ |  | 4 | 0 |  |  | 4 | 4 | 4 | 4 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | 1 | Implement different weapons and decide which one to use | YZ |  | 9 | 0 |  |  | 9 | 9 | 9 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ball and chain for fettered prisoner / hammer
4 | 1 | Refine the design to make it more innovative | YZ |  | 4 | 0 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | use joystick to control the move of hammer
5 | 2 | Play similiar games | YZ |  | 4 | 0 |  |  | 4 | 4 | 4 | 4 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | 1 | Write research analysis | YZ |  | 6 | 0 |  |  | 6 | 6 | 6 | 4 | 4 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Character | YZ
7 | 1 | Detailed design of hammer movement | YZ |  | 5 | 0 |  |  | 5 | 5 | 5 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | 2 | Hit using keyboard | YZ |  | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | 2 | Jump using keyboard | YZ |  | 8 | 0 |  |  | 8 | 8 | 8 | 8 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | 1 | Joystick configuration and motion detection | YZ |  | 8 | 0 |  |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | 2 | Hit using joystick | YZ |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | 2 | Jump using joystick | YZ |  | 4 | 2 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
13 | 2 | Walk in single side | YZ |  | 1 |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | 2 | Walk when changing side | YZ |  | 4 |  |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
|  | Enemy | YZ
15 | 1 | Enemy A | YZ |  | 6 | 6 |  |  | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
16 | 2 | Emeny B | YZ |  | 4 | 4 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
17 | 2 | Enemy C | YZ |  | 4 | 4 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
21 | 3 | Enemy placement | YZ |  | 6 | 6 |  |  | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
|  | Environment | YZ
18 | 2 | Camera movement on single side | YZ |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | 2 | Camera movement when changing side | YZ |  | 6 | 6 |  |  | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
20 | 2 | Map | YZ |  | 8 | 8 |  |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
Bugs to be Fixed!!! | [24 empty] | Fix Description (if unusual or useful to later generations) | Status
107 | [25 empty] | Reported
108 | [25 empty] | Reported
109 | [25 empty] | Reported
110 | [25 empty] | Reported
111 | [25 empty] | Reported
112 | [25 empty] | Reported
113 | [25 empty] | Reported
114 | [25 empty] | Reported
115 | [25 empty] | Reported
116 | [25 empty] | Reported
117 | [25 empty] | Reported
118 | [25 empty] | Reported
119 | [25 empty] | Reported
120 | [25 empty] | Reported
121 | [25 empty] | Reported
122 | [25 empty] | Reported
123 | [25 empty] | Reported
124 | [25 empty] | Reported
125 | [25 empty] | Reported
126 | [25 empty] | Reported
127 | [25 empty] | Reported
128 | [25 empty] | Reported
129 | [25 empty] | Reported
130 | [25 empty] | Reported
131 | [25 empty] | Reported
132 | [25 empty] | Reported
133 | [25 empty] | Reported
134 | [25 empty] | Reported
135 | [25 empty] | Reported
136 | [25 empty] | Reported
137 | [25 empty] | Reported
138 | [25 empty] | Reported
139 | [25 empty] | Reported
140 | [25 empty] | Reported
141 | [25 empty] | Reported
142 | [25 empty] | Reported
143 | [25 empty] | Reported
144 | [25 empty] | Reported
145 | [25 empty] | Reported
146 | [25 empty] | Reported
147 | [25 empty] | Reported
148 | [25 empty] | Reported
149 | [25 empty] | Reported
150 | [25 empty] | Reported
151 | [25 empty] | Reported
152 | [25 empty] | Reported
153 | [25 empty] | Reported
154 | [25 empty] | Reported
155 | [25 empty] | Reported
156 | [25 empty] | Reported
157 | [25 empty] | Reported
158 | [25 empty] | Reported
159 | [25 empty] | Reported
160 | [25 empty] | Reported
161 | [25 empty] | Reported
162 | [25 empty] | Reported
163 | [25 empty] | Reported
164 | [25 empty] | Reported
165 | [25 empty] | Reported
166 | [25 empty] | Reported
167 | [25 empty] | Reported
168 | [25 empty] | Reported
169 | [25 empty] | Reported
170 | [25 empty] | Reported
171 | [25 empty] | Reported
172 | [25 empty] | Reported
173 | [25 empty] | Reported
174 | [25 empty] | Reported
175 | [25 empty] | Reported
176 | [25 empty] | Reported
177 | [25 empty] | Reported
178 | [25 empty] | Reported
179 | [25 empty] | Reported
180 | [25 empty] | Reported
181 | [25 empty] | Reported
182 | [25 empty] | Reported
183 | [25 empty] | Reported
184 | [25 empty] | Reported
185 | [25 empty] | Reported
186 | [25 empty] | Reported
187 | [25 empty] | Reported
188 | [25 empty] | Reported
189 | [25 empty] | Reported
190 | [25 empty] | Reported
191 | [25 empty] | Reported
192 | [25 empty] | Reported
193 | [25 empty] | Reported
194 | [25 empty] | Reported
195 | [25 empty] | Reported
196 | [25 empty] | Reported
197 | [25 empty] | Reported
198 | [25 empty] | Reported
199 | [25 empty] | Reported
200 | [25 empty] | Reported
201 | [25 empty] | Reported
202 | [25 empty] | Reported
203 | [25 empty] | Reported
204 | [25 empty] | Reported
205 | [25 empty] | Reported
206 | [25 empty] | Reported
207
208
Interpreted Data
210 |  | Days | [6 empty] | 14 | 14 | 13 | 12 | 11 | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0
211 |  | Optimum | [5 empty] | Line | 106 | 106 | 98.4286 | 90.8571 | 83.2857 | 75.7143 | 68.1429 | 60.5714 | 53 | 45.4286 | 37.8571 | 30.2857 | 22.7143 | 15.1429 | 7.5714 | 0
212
213 |  | Sum | [6 empty] | 104 | 104 | 104 | 104 | 104 | 104 | 104 | 104 | 104 | 0 | 0 | 0 | 0 | 0 | 0 | 0
214 |  | Rank (and not reduced to 0 after today)
215 |  | Rank 1 - The MOST important | 1 | [5 empty] | 46 | 44 | 44 | 39 | 32 | 24 | 19 | 8 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
216 |  |  | 2 | [5 empty] | 54 | 54 | 54 | 54 | 51 | 42 | 36 | 33 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28
217 |  |  | 3 | [5 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
218 |  |  | 4 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
219 |  | Rank 5 - The LEAST important | 5 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
220
221 |  | Assigned (Replace these with your team members!)
222 |  | Yujin Zhang | YZ |  |  |  |  | YZ | 106 | 104 | 104 | 99 | 89 | 72 | 61 | 47 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
227 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
228 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
229 | [7 empty] | Unassigned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
230 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
231 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
232 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
233
234
235 | [7 empty] | DateLine | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 0 | 0 | 0 | 0 | 0 | 0 | 0
236

## Daily Scrum
Producer | 2017-02-08 |  | Team Members
Approved | Dates |  | Yujin Zhang
| 2017-02-01 | Wed | Done: thinking about game mechanism
| 2017-02-02 | Thu | Done: thinking about game mechanism
| 2017-02-03 | Fri | Done: thinking about game mechanism
| 2017-02-04 | Sat | Done: thinking about game mechanism
| 2017-02-05 | Sun | Done: decided basic idea of the game, started playing similiar games
| 2017-02-06 | Mon | Done: basic movement: hit back and forth, switch length of hammer rod, jump Next: turn left/right, research analysis
| 2017-02-07 | Tue | Done: joystick configuration. Refined the idea of character movement.
| 2017-02-08 | Wed | Done: joystick movement, R&A
| 2017-02-09 | Thu
| 2017-02-10 | Fri
| 2017-02-11 | Sat
| 2017-02-12 | Sun
| 2017-02-13 | Mon
| 2017-02-14 | Tue
| 2017-02-15 | Wed
| 2017-02-16 | Thu
| 2017-02-17 | Fri
| 2017-02-18 | Sat
| 2017-02-19 | Sun
| 2017-02-20 | Mon
| 2017-02-21 | Tue
| 2017-02-22 | Wed